## Read me
M365 AI Agent Hardening Kit: Top 5
Version | 1.0 (2026-10-28; facts re-read on Microsoft Learn 2026-10-24, AG02 and AG05 again 2026-10-28; validated: quality gate, read-only guard, PowerShell 7.4 parse, Excel recalc)
What this is | The same backlog as the Jira CSV, as a project plan for teams without Jira. One row per control on 'Project plan'; 'Dashboard' shows progress.
Your cells | Yellow cells on 'Project plan': Owner, Start, Due, Status, Done date, Notes. Everything else is filled in or calculated.
Status values | To do, In progress, Blocked, Done, Not applicable. Pick from the drop-down.
% complete | Done = 100%. In progress = 50% (assumption: a simple midpoint, so the dashboard moves before a control is finished). Everything else = 0%. 'Not applicable' rows are left out of the totals.
Effort (h) | Hands-on hours from the guide: upper end of a range, minutes converted to hours. Waiting time (DNS, rollout weeks, recurring reviews) is not included.
Overdue | Due date before today and status not Done or Not applicable.
Example row | Owner: j.doe · Start: 03/11/2026 · Due: 07/11/2026 · Status: In progress · Done date: (empty until Done) · Notes: Report-only since 03/11, review on 06/11.
Details per control | Why, steps, read-only check, verify, licence and sources are in the guide (.md) that ships in the same zip.
Disclaimer | Not affiliated with or endorsed by Microsoft. Test every change in Report-only or on a pilot group first.

## Dashboard
M365 AI Agent Hardening Kit: Top 5 — progress
All figures are formulas over 'Project plan'. 'Not applicable' rows are excluded from % complete.
By area
Area | Controls | Done | In progress | Blocked | Not applicable | % complete | Overdue | Hours left
Agent inventory & monitoring
Copilot Studio guardrails
Agent identities (Microsoft Entra Agent ID)
Total
By sprint
Sprint | Controls | Done | In progress | Blocked | Not applicable | % complete | Overdue | Hours left
Sprint 1 - AI agent baseline
Total

## Project plan
ID | Control | Area | Sprint | Priority | Effort (guide) | Effort (h) | Licence | Owner | Start | Due | Status | Done date | % complete | Overdue | Verify (done when…) | Notes
AG01 | Inventory every agent in the tenant | Agent inventory & monitoring | Sprint 1 - AI agent baseline | Highest | 1 h | 1 | Any Microsoft 365 tenant. Inventory: Power Platform administrator, Global reader, or AI reader. Agent identities: AgentIdentity.Read.All (Agent ID Administrator for non-owners). |  |  |  | To do |  |  |  | Every Copilot Studio agent and every agent identity has an owner and a purpose recorded in the tracker.
AG02 | Require user authentication for Copilot Studio agents | Copilot Studio guardrails | Sprint 1 - AI agent baseline | Highest | 30 min | 0.5 | Power Platform admin (included with Copilot Studio) |  |  |  | To do |  |  |  | Trying to publish a test agent with No authentication fails with a data policy error.
AG03 | Block HTTP requests and channels you don't use | Copilot Studio guardrails | Sprint 1 - AI agent baseline | High | 1 h | 1 | Power Platform admin (included with Copilot Studio) |  |  |  | To do |  |  |  | In the data policy, HTTP is blocked or endpoint-filtered, and every channel not on your approved list is in the Blocked group.
AG04 | Watch agent creation, publishing, sharing and authentication changes | Agent inventory & monitoring | Sprint 1 - AI agent baseline | High | 1 h | 1 | Microsoft 365 audit (Standard). Users need an assigned Microsoft 365 licence for Copilot Studio events to be recorded. |  |  |  | To do |  |  |  | A saved audit search (or SIEM rule) exists for the five operations, and last week's events were reviewed.
AG05 | Block high-risk agent identities with Conditional Access | Agent identities (Microsoft Entra Agent ID) | Sprint 1 - AI agent baseline | High | 30 min | 0.5 | Microsoft Agent 365 + Entra ID P2 or Microsoft 365 E5 (risk-based), or Microsoft 365 E7. Agent risk is in preview. |  |  |  | To do |  |  |  | A policy targeting All agent identities with Agent risk = High and Block exists and is On (state: enabled) after the Report-only review.
Formulas:
Overdue = IF(AND(ISNUMBER([Due]),[Due]<TODAY(),[Status]<>"Done",[Status]<>"Not applicable"),"Yes","")